## FR ROADMAP-Draft 0
GLOBAL FUND CCM ZAMBIA NFM4 FR ROADMAP WINDOW 2
Activity Description | Leading responsibility | Funding source | Product | Comments | September 2013 |  |  |  | October 2013 |  |  |  | November 2013 |  |  |  | 2022-12-01 |  |  |  | 2023-01-01 |  |  |  | 2023-02-01 |  |  |  | 2023-03-01 |  |  |  | 2023-04-01 |  |  |  | 2023-05-01 |  |  |  | June 2014 |  |  |  | July 2014 |  |  |  | 2014-07-01 |  |  |  | 2014-08-01 |  |  |  | 2014-09-01 |  |  |  | 2014-10-01 |  |  |  | 2014-11-01 |  |  |  | 2014-12-01 |  |  |  | Comments | Budget (ZMK)
[5 empty] | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 |  | CCM | OTHERS | TOTAL
CCM TTT-Process of Assessment and selection of PRs | CCM Oversight Committee | CCM | Report | bar: 2022-12-01 WK 1 to 2023-03-01 WK4
Country Allocation Letter | GFCT | - | Letter | bar: 2022-12-01 WK 2
Draft FR Concept Note | CCM Sec |  | FR Concept Note | [72 empty] | 0 | bar: 2022-12-01 WK3
Draft ToR for FR TAs | CCM Sec |  | ToR for lead and costing cosultants | bar: 2022-12-01 WK4 to 2023-01-01 WK 1
Draft ToR for WT & RT | CCM Sec |  | ToR/Members' profile/CoI procedures | bar: 2022-12-01 WK4 to 2023-01-01 WK 1
Draft CoI procedures for WT & RT | CCM Sec |  | ToR/Members' profile/CoI procedures | bar: 2023-01-01 WK 1
Internal Reviews | CCM Sec |  | above stated documents | bar: 2023-01-01 WK 1 to 2023-01-01 WK 2
Draft NFM4 Roadmap | CCM Sec |  | Roadmap | bar: 2023-01-01 WK3
Share roadmap with the CCM Stakeholders | CCM Sec |  | Roadmap | bar: 2023-01-01 WK4
Submit above documents to the CCM for review & feedaback | CCM Sec |  | Concept Note, WT, RT, CoI procedures, road map | bar: 2023-01-01 WK4
Electronic endorsement of documents by CCM | CCM Members |  | Stated documents endorsed | bar: 2023-02-01 WK 1
Develop WT & RT composition guide based on NFM4 Modular Framework and formally request for WT & RT lists | CCM Sec |  | Composition guide and request letters | bar: 2023-01-01 WK4
Constitute and submit WT to Sec | Leads: CCM CSOs/MoH - PR/CHAZ -PR/Govt line Ministries/CPs |  | WT list | bar: 2023-02-01 WK 1
Constitute and submit RT to Sec | Leads: USG/UN CPs |  | RT list | bar: 2023-02-01 WK 1
Share TA ToRs With UNAIDS | CCM Sec |  | TA ToRs | bar: 2023-02-01 WK 1
NFM4 Country Dialogues - 1 (Province) | CCM Sec | GRZ co-funding | Reports | bar: 2023-02-01 WK 2
NFM4 WT Retreat - 1 | WT Leads | MoH | Draft 1 | bar: 2023-02-01 WK3
NFM4 RT - 1 | RT Leads | - | Revised Draft 1 | bar: 2023-02-01 WK4
Contracting FR TA | CPs: UNAIDS/WHO/UNFPA/Equip Zambia/GIZ/StopTB/RollBack Malaria |  | Signed contracts | bar: 2023-02-01 WK4
NFM4 WT Retreat - 2 | WT Leads | MoH | Draft 2 | bar: 2023-03-01 WK 1
NFM4 RT - 2 | RT Leads | - | Revised Draft 2 | bar: 2023-03-01 WK 2
NFM4 Country Dialogues 2 - (Lusaka based Constituency Consultative meetings) | CCM Sec | CPs | Constituency Minutes | bar: 2023-03-01 WK 2
CCM ADHOC Meeting - Update on Draft 2 | CCM Sec | CCM | Revised Draft 2 | bar: 2023-03-01 WK3
Receive HIV/AIDS, TB & Malaria National Strategic Plans and COVID-19 Preparedness and Suatainability Plan | CCM Sec |  | National Disease Program Managers | bar: 2023-02-01 WK 1 to 2023-03-01 WK4
Finalization and validation of HIV/AIDS, Malaria and TB National strategic plans and COVID-19 Preparedness and Sustainability Plan | NAC/MoH/NMEC/ZNPHI |  | Revised NSPs, COVID-19 Plan (costed gap analysis) | [72 empty] | 0 | bar: 2023-03-01 WK3 to 2023-03-01 WK4
Finalization and validation of strategic documents supported by CPs | UN/USG/GIZ/EU/WB/CHAI/etc |  | Evidence support documents | bar: 2023-03-01 WK 1 to 2023-03-01 WK4
NFM4 WT Retreat - 3 | WT Leads | MoH | Draft 3 | bar: 2023-04-01 WK 1
NFM4 RT - 3 | RT Leads | - | Revised Draft 3 | bar: 2023-04-01 WK 2
NFM4 Country Dialogues - 3 (Province) | CCM Sec | GRZ co-funding | Reports | bar: 2023-04-01 WK 2
NFM4 WT Retreat - 4 | WT Leads | MoH | Draft 4 | bar: 2023-04-01 WK4
NFM4 RT - 4 | RT Leads | - | Revised Draft 4 | bar: 2023-05-01 WK 1
CCM ADHOC Meeting - Update on Draft 4 | CCM Sec | CCM | Revised Draft 4 | bar: 2023-05-01 WK 1
NFM4 - WTs, RTs, Stakeholder and National Validation - Core/small Retreat 5 . Uploading documents | CCM Sec/WT Leads/Consultants | MoH | Draft 5 | bar: 2023-05-01 WK 2
CCM ADHOC Meeting - Staholder and National Validation | CCM Sec | CCM | Validated NFM4 | bar: 2023-05-01 WK 2
NFM4 - Core WTs Leads/Consultants - Core/small Retreat 5 . Uploading documents | CCM Sec/WT Leads/Consultants | MoH | Finalized NFM4 FR | bar: 2023-05-01 WK3
Submission of NFM4 FR | CCM Sec | - | NFM4 FR endorsed and submitted | bar: 2023-03-01 WK 1; 2023-05-01 WK4
|  |  |  | this feedback needs to be provided to the HIV TTT | [70 empty] | 55000 | 55000
[75 empty] | 0 | 0
|  |  |  | CCM to review HIV CN draft (2) and be ready to discuss at the CCM meeting | [70 empty] | 0 | 0
[75 empty] | 0 | 0
|  |  |  | final edits generated from CCM FY14 Q2 meeting incorporated and then circulated for CCM electronica approval | [70 empty] | 0 | 0 | bar: June 2014 WK 1
[75 empty] | 0 | 0 | bar: June 2014 WK 1

## FR ROADMAP-2 (hidden)
GLOBAL FUND NFM CONCEPT NOTE ROADMAP
Activity Description | Leading responsibility | Funding source | Product | Comments | September 2013 |  |  |  | October 2013 |  |  |  | November 2013 |  |  |  |  | December 2013 |  |  |  | January 2014 |  |  |  | February 2014 |  |  |  | March 2014 |  |  |  | April 2014 |  |  |  | May 2014 |  |  |  | June 2014 |  |  |  | July 2014 |  |  |  | 2014-07-01 |  |  |  | 2014-08-01 |  |  |  | 2014-09-01 |  |  |  | 2014-10-01 |  |  |  | 2014-11-01 |  |  |  | 2014-12-01 |  |  |  | Comments |  | Budget (ZMK)
[5 empty] | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | Time frame | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 | WK 1 | WK 2 | WK3 | WK4 |  | Status | CCM | OTHERS | TOTAL
[77 empty] | 0 | 0
Revised HIV/AIDS, Malaria and TB National strategic plans finalised and validated | NAC /MCDMCH /MOH |  | Revised NSPs(costed gap analysis) | [13 empty] | 31st Jan.2014 | [60 empty] | 0 | bar: December 2013 WK 1 to January 2014 WK4
Revised HIV/AIDS, Malaria and TB NSPs reviewed by CCM and other partners | SPI Co | CCM | CCM informed of the content of Revised NSPs and the next steps regarding priority setting | [13 empty] | By 10th Feb.2014 | [58 empty] | 14000 |  | 14000 | bar: February 2014 WK 1 to February 2014 WK 2
HIV / TB & Malaria Technical Task Teams (TTT) Established | CCM |  | TOR (including membership) developed and approved by CCM) | [13 empty] | By 15th Feb.2014 | [58 empty] | 0 |  | 0 | bar: February 2014 WK 2
HIV/TB/ Malaria Concept Note (CN) Writing Team Established | CCM |  | TOR should be part of the HIV/TB/ Malaria TTT TOR | This smaller Writing Team should be a subgroup of the HIV /TB TTT | [12 empty] | By 15th Feb.2014 | [58 empty] | 0 |  | 0 | bar: February 2014 WK 2
Engage CN writing consultants by disease ( 3 X 2 ) | [16 empty] | By 10th April 2014 | [59 empty] | 495000 | 495000 | bar: April 2014 WK 2
Review Revised NSPs and establish funding priority recommendations to be considered and approved by Full CCM | HIV /TB/ Malaria writing team | CCM Stakeholder meeting budget | [14 empty] | 28th Feb.2014 | [58 empty] | 55000 |  | 55000 | bar: February 2014 WK 1 to February 2014 WK4
Disease priority recommendations presented and approved by CCM | SPI Co | CCM SPI/OVC budget |  | SPI should use their FY14 Q1 Meeting to finalize HIV priorities, these should be approved by the EXCO and then officially presented and endorsed by CCM at the FY14 Q1 full CCM Meeting | [12 empty] | 10th Mar. 2014 | [58 empty] | 15000 |  | 15000 | bar: March 2014 WK 1
Constituencies review and provide feedback on approved priority areas (all diseases) | CCM Constituency Members | Constituency meeting budget | meeting minutes serving as written feedback on HIV/TB/Malaria priority areas | this written feedback needs to be provided to the HIV TTT to be incorporated into CN development | [12 empty] | By 21st mar.2014 | [58 empty] | 99000 |  | 99000 | bar: March 2014 WK 2 to March 2014 WK3
Ad-hoc stakeholder feedback collection | CCM Secretariat |  | documented feedback | CCM Secretariat will be available to present approved priorities when invited by stakeholders (e.g. CP meetings, TWGs, etc.) | [12 empty] | 1st Mar. upto 30th Apr.2014 | [58 empty] | 0 |  | 0 | bar: March 2014 WK4 to May 2014 WK 1
NFM Funding Level Announced | TGF-Geneva | [15 empty] | By 31st mar.2014 | [58 empty] | 0 | 0 | 0 | bar: March 2014 WK 1 to March 2014 WK4
HIV /TB / Malaria TTT develops final prioritization recommendations based on NFM funding level (including incentive funding) | HIV / TB / Malaria TTT | CCM Alignment meeting budget | Disease prioritization recommendation (reviewed/revised based on funding announcement) | SPI CCM lead is responsible for calling and facilitating this meeting | [12 empty] | 3rd Apr.2014 | [59 empty] | 22000 | 22000 | bar: April 2014 WK 1
Extraordinary (1) CCM Meeting | CCM | CCM Meeting budget | final HIV/TB/Malaria prioritization based on availability of HIV NFM funds | this timeline could shift based on geneva announcement timeline, goal is to call an extraordinary meeting within 1-2 weeks of announcement | [12 empty] | 10 Apr.2014 | April 2014 WK 1: EXCO; April 2014 WK 2: CCM |  |  | 14000 |  | 14000
HIV/ TB / Malaria CN Writing Retreat | NAC / HIV /TB TTT |  | complete first draft of CN | feedback from constituencies and CCM to be provided for writing retreat | [12 empty] | 14th Apr.2014 | [59 empty] | 55000 | 55000 | bar: April 2014 WK3
CCM Electronic review of HIV CN draft (1) | CCM |  | documented CCM feedback | this feedback needs to be provided to the HIV TTT | [12 empty] | 29th Apr.2014 | [59 empty] | 0 | 0 | bar: April 2014 WK4
Stakeholder meeting to review CN draft (1)-all diseases | CCM Secretariat | PEPFAR | documented stakehodler feedback on HIV /TB/Malaria CN | this feedback needs to be provided to the HIV TTT | [12 empty] | 6th May 2014 | [59 empty] | 55000 | 55000 | bar: April 2014 WK4
HIV/TB / Malaria TTT develops HIV CN draft (2) | NAC / HIV /TB/Malaria TTT |  | complete second draft of HIV/TB/Malaria CN | [13 empty] | 13th May,2013 | [59 empty] | 0 | 0 | bar: May 2014 WK 1
CCM Electronic review of CN draft (2) | CCM |  |  | CCM to review HIV CN draft (2) and be ready to discuss at the CCM meeting | [12 empty] | 13th May,2013 | [59 empty] | 0 | 0 | bar: May 2014 WK 2
CCM electronic approval of CN | CCM | [15 empty] | 20th May,2013 | May 2014 WK 2: SPI; May 2014 WK3: EXCO |  |  |  | 0 | 0
Final CN circulated for CCM signature | CCM Secretariat |  |  | final edits generated from CCM FY14 Q2 meeting incorporated and then circulated for CCM electronica approval | [12 empty] | 20th May,2013 | [59 empty] | 0 | 0 | bar: May 2014 WK3; June 2014 WK 1
CN Submitted | CCM Secretariat | [15 empty] | 27th May,2013 | [59 empty] | 0 | 0 | bar: May 2014 WK4 to June 2014 WK 1

## FR - Summary budget (hidden)
GLOBAL FUND NFM CN SUMMARY BUDGET BY ACTIVITY | Budget (ZMK)
| CCM | OTHERS | TOTAL
1. CCM Meeting (Revised NSPs reviewed by CCM) | 14000 |  | 14000
4. HIV / TB Technical Task Team (TTT) Established | 0 |  | 0
5. HIV/TB Concept Note (CN) Writing Team Established | 0 |  | 0
6. Stakeholders meeting- |  |  | 0
- Review of disease priority areas | 55000 |  | 55000
- Review of draft 1 Concept note |  | 55000 | 55000
7. CCM Oversight budget (Disease priority recommendations integrated and approved by CCM) | 15000 |  | 15000
8. Constituency meetings to review and provide feedback for all diseases | 99000 |  | 99000
9. TTT's to develop final HIV /TB /Malaria service prioritization based on NFM funding level |  | 22000 | 22000
10.Extraordinary (1) CCM Meeting | 14000 |  | 14000
11.HIV/ TB CN Writing Retreat |  | 55000 | 55000
13.Consultants for CN writing X 3 X 2@k2,750 X 30 DAYS |  | 495000 | 495000
TOTAL BUDGET: | 197000 | 627000 | 824000
FUNDS AVAILABLE: | CCM | OTHERS | TOTAL
CCM | 197000
PEPFAR |  | 77000
TOTAL FUNDS AVAILABLE: | 197000 | 77000 | 274000
FUNDING GAP: | CCM | OTHERS | TOTAL
| 0 | 550000 | 550000

## CN-detailed costs (hidden)
GLOBAL FUND NFM CN
| Activity description | Product | Leading responsibility | Funding source | Budget Amount in zmk
1 | NASF concept note developed | Revised NASF(costed gap analysis) | NAC | NAC | 0
| Revised NASF finalised and validated | Revised NASF(costed gap analysis) | NAC | NAC | 0
2 | Revised NASF reviewed by CCM | CCM informed of the content of R NASF and the next steps regarding priority setting | CCM | CCM budget | 14000
3 | HIV / TB Technical Task Team (TTT) Established | TOR (including membership) developed and approved by CCM) | CCM |  | 0
4 | HIV/TB Concept Note (CN) Writing Team Established | TOR should be part of the HIV/TB TTT TOR | CCM |  | 0
| Engage HIV/TB CN writing consultants X 3 | TOR should be part of the HIV/TB TTT TOR |  |  | 495000
5 | Review Revised NASF and establish funding priority recommendations to be considered and approved by CCM and other stakeholders |  | HIV /TB writing team | CCM budget | 55000
6 | HIV priority recommendations presented and approved by CCM |  | SPI & OV Committee | CCM budget | 15000
7 | Constituencies review and provide feedback on approved priority areas (all diseases) | meeting minutes serving as written feedback on HIV priority areas | CCM Constituency Members | CCM budget | 99000
8 | Ad-hoc stakeholder feedback collection | documented feedback | CCM Secretariat |  | 0
9 | NFM Funding Level Announced |  | TGF-Geneva
10 | HIV / TB TTT develops final HIV service prioritization recommendations based on HIV/TB NFM funding level (including incentive funding) | HIV prioritization recommendation (reviewed/revised based on funding announcement) | HIV / TB TTT | CCM budget | 55000
11 | Extraordinary (1) CCM Meeting | final HIV service prioritization based on availability of HIV NFM funds | CCM | CCM budget | 14000
12 | HIV/ TB CN Writing Retreat | complete first draft of HIV CN | NAC / HIV /TB TTT |  | 55000
13 | CCM Electronic review of HIV CN draft (1) | documented CCM feedback | CCM |  | 0
14 | Stakeholder meeting to review CN draft (1)-all diseases | documented stakehodler feedback on HIV CN | CCM Secretariat | PEPFAR | 22000
15 | HIV/TB TTT develops HIV CN draft (2) | complete second draft of HIV CN | NAC / HIV /TB TTT |  | 13000
16 | CCM Electronic review of HIV CN draft (2) |  | CCM |  | 0
17 | CCM electronic approval of HIV CN |  | CCM |  | 0
18 | Final HIV CN circulated for CCM signature |  | CCM Secretariat |  | 0
19 | HIV CN Submitted |  | CCM Secretariat |  | 0
| Total budget |  |  |  | 837000